## Sheet1
Hospital Outpatient Department (HOPD) Practice Startup Checklist:
Contractual milestones
Task number | Task | Owner | Progress | Date scheduled | Date complete
1 | Create a fully executed employment agreement between the hospital and the physicians.
2 | In a corporate medicine state, ensure that the tax-exempt facility is in full legal compliance with state medical board requirements for creating a Professional Services Corporation led by licensed physicians.
3 | In a corporate practice of medicine state, create a fully executed Professional Services Contract between the hospital and the physicians.
4 | Confirm that either of the required agreements adequately address the obligations of the hospital and the obligations of the physician to establish and participate in the HOPD.
Credentialing milestones
Task number | Task | Owner | Progress | Date scheduled | Date complete
1 | Obtain hospital medical staff privileges for the physicians from the medical staff office.
2 | Enroll physicians in payer contracts and align contracts for both facility billing and professional billing.
Financial reporting milestones
Task number | Task | Owner | Progress | Date scheduled | Date complete
1 | Confirm a budget for pre-opening expenses as well as ongoing operational expenses tied to the pro forma.
2 | Establish a cost center for operational revenue and expenses.
3 | If necessary in a corporate medicine state, create a subsidiary cost center that complies with state law to report professional revenue.
4 | Establish a separate tax ID number for the employed practice.
5 | Create fair market value (FMV) daily clinic charge for independent physicians.
Space and equipment milestones
Task number | Task | Owner | Progress | Date scheduled | Date complete
1 | If purchasing a practice, hospital will inventory any existing furniture and medical equipment to be purchased from the practice.
2 | Ensure that all purchased furniture and equipment from the practice meets Joint Commission and other regulatory standards.
3 | If not purchasing existing furniture, the practice will be responsible for moving it out of the clinic at its expense prior to the clinic opening.
4 | Purchase all necessary furniture and medical equipment in accordance with hospital polices.
5 | Ensure all purchased equipment (existing and new) is in service as expected.
6 | Provide signage, including a new clinic door sign and directory information.
7 | Display a poster for the clinic lobby welcoming patients.
8 | Display regulatory signs mandated by the state and CMS for a hospital department.
Staffing milestones
Task number | Task | Owner | Progress | Date scheduled | Date complete
1 | Agree to the number and mix of clinic and support staff.
2 | Utilize hospital job descriptions and establish new ones if necessary.
3 | If hiring private practice employees, determine disposition of current PTO/longevity and whether there will be a buy-out or rollover.
4 | Allot time prior to the clinic opening for orientation and training.
5 | Provide facility new employee orientation and pre-employment physicals.
6 | Provide EHR training.
7 | Adopt and orient staff on all clinic processes and procedures.
Medical records milestones
Task number | Task | Owner | Progress | Date scheduled | Date complete
1 | Existing medical records are the property of the practice, and the practice will maintain those records at its expense.
2 | The hospital’s Health Information Management Department will have authority over the new clinic’s medical records.
3 | Every patient will be considered a new patient with a new medical record.
Provider templates/schedule milestones
Task number | Task | Owner | Progress | Date scheduled | Date complete
1 | Establish new provider templates with appointment types and durations.
2 | Provide templates for each physician, nurse and technician if necessary, including which type of appointment goes at which time.
3 | Transfer current patients and appointments from the existing practice to the new system.
Front office procedure milestones
Task number | Task | Owner | Progress | Date scheduled | Date complete
1 | Confirm and train on all registration, scheduling, check-in and checkout duties.
2 | Collect all necessary forms for hospital outpatient clinic, which will be different from those in a private practice.
3 | Patients will receive and sign an acknowledgment form confirming that they understand the transition from a private practice to an outpatient hospital department and the effect it has on their financial responsibility.
4 | Provide consent to treat authorization form for both the hospital and the physician.
5 | Create and train on the payment policy.
6 | Create and train on the no-show policy.
Clinical staff procedure milestones
Task number | Task | Owner | Progress | Date scheduled | Date complete
1 | Confirm and train on triage procedures.
2 | Confirm and train on patient rooming procedures.
3 | Confirm and train on the advanced beneficiary notice process.
4 | Confirm and train on the point of care procedures.
5 | Ensure a CLIA license is in place.
Provider-based billing milestones
Task number | Task | Owner | Progress | Date scheduled | Date complete
1 | Create a professional billing fee schedule for physician charges.
2 | Create a separate facility charge master that includes clinic visit, procedures, vaccines, medication and point of care laboratory charges.
3 | Enable the billing system to “clone” the professional charge to create a corresponding visit and procedure facility charge.
4 | Route facility charges to the hospital cost center and professional charges to the physician group cost center.
5 | Enable and train billing staff and clinic staff to track facility and professional accounts receivable effectively.
Financial office procedures
Task number | Task | Owner | Progress | Date scheduled | Date complete
1 | Physicians must be fully credentialed with government and commercial payers and the practice must be able to bill and collect from each.
2 | Confirm and train on the process for incoming and outgoing referrals and authorizations.
3 | Confirm and train on the process for scheduling ancillary tests.
4 | Confirm and train on the daily deposit process.
5 | Validate the hospital charge master and the professional fee schedule.
6 | Ensure charge capture for both hospital and professional services.
7 | Enable and train front desk staff to take both professional and facility payments.
Patient flow milestones
Task number | Task | Owner | Progress | Date scheduled | Date complete
1 | Review registration/check-in workflow.
2 | Review triage workflow.
3 | Review exam room workflow.
4 | Review point of care tests workflow.
5 | Review physician workflow.
6 | Review referral workflow.
7 | Review follow-up appointment workflow.
Patient and provider correspondence milestones
Task number | Task | Owner | Progress | Date scheduled | Date complete
1 | Draft a welcome letter to existing patients notifying them of the change in practice.
2 | Draft a letter to referring physicians and the hospital medical staff advising them of the change in practice.
3 | Articulate the patient referral process for outside providers.
Marketing milestones
Task number | Task | Owner | Progress | Date scheduled | Date complete
1 | Provide content to the website team and ensure the website is accurate and active in conjunction with the clinic opening.
2 | Utilize the facilities' current social media platforms to promote the clinic.
3 | Create and print clinic brochures.
4 | Make appointments to visit referring physicians and communicate referral process.
5 | Schedule outreach events in the community.
Information technology milestones
Task number | Task | Owner | Progress | Date scheduled | Date complete
1 | Ensure all necessary computers, printers, telephones, fax machines and scanners are purchased new to comply with hospital standards.
2 | Hospital information services department will have authority over network access and internet connectivity for the practice.
3 | Ensure that all staff have computer access in place prior to the clinic opening.
Environment of care milestones
Task number | Task | Owner | Progress | Date scheduled | Date complete
1 | Comply with all The Joint Commission requirements.
2 | Schedule staff to clean the area and empty trash after hours.
3 | Ensure compliance with all hospital infection prevention policies and procedures.
4 | Conduct a safety inspection to ensure compliance with all state and federal regulations.
5 | Order bins for confidential information disposal and schedule service for those bins.
Pharmacy milestones
Task number | Task | Owner | Progress | Date scheduled | Date complete
1 | If a pharmacist is deployed in the clinic, he or she shall have a collaboration agreement executed with the clinic physicians before seeing patients.
2 | Ensure sample medications are secured and a policy/procedure is in place to distribute sample medications.
3 | The pharmacist will have his or her own provider template, appointment types and patient schedule.
Routine purchasing milestones
Task number | Task | Owner | Progress | Date scheduled | Date complete
1 | Contact Purchasing to set up an account with the office supply vendor, including cost center, delivery location, username and password.
2 | Establish a process for ordering medical supplies consistent with other hospital departments.
Physical plant milestones
Task number | Task | Owner | Progress | Date scheduled | Date complete
1 | Contact Physical Plant to key the entire clinic, including doors, desks and overhead shelving.
Outside vendor contract milestones
Task number | Task | Owner | Progress | Date scheduled | Date complete
1 | Inventory all outside vendor contracts and notify the points of contact of the new clinic.
2 | Coordinate with hospital Legal Affairs to evaluate if a new contract must be executed under the new Provider Services Agreement.
3 | Create a policy/process for all outside company representatives, including pharmacy and medical device reps.